## ورقة1
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Manual stock registers or basic spreadsheets; no real-time stock visibility; expiry dates and batch numbers tracked by hand; frequent stock-outs and billing errors. | Web/desktop POS and inventory system with database (MySQL/PostgreSQL); barcode scanning; batch and expiry tracking; low-stock alerts; cloud backup. | ✅ Technically feasible
Operational | Manual billing and stock counts are time-consuming; difficulty tracking expiry dates and batches; resistance to change possible. | Faster sales and dispensing; automatic stock deduction on every sale; expiry and reorder alerts; reduced workload; better customer service. | ✅ Operationally feasible
Economic | Cost of software, hardware (barcode scanners, receipt printer), training, and maintenance. | Saves time/money; fewer losses from expired and out-of-stock medicines; reduces errors; lower admin costs; long-term efficiency gains. | ✅ Cost-effective
Legal | Need compliance with pharmacy/drug regulations (e.g., prescription and controlled-substance records) and patient data protection laws. | Keep an audit trail of sales and stock movements; role-based access; implement data privacy/security policies; ensure regulatory compliance. | ✅ Legally feasible
Schedule | Manual processes delay reporting, reordering, and customer service. | Estimated timeline 3–6 months (requirements → design → development → testing → deployment). | ✅ Achievable timeline

## ورقة2
Cost–Benefit Analysis – Pharmacy Sales & Stock Management System
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | Development (in-house) or purchase of pharmacy POS/inventory software license | $2,000 – $4,500 | Centralized, automated sales and stock tracking reduces errors, delays and expired stock. | $3,500 savings in billing, stock and expiry errors
Hardware | Server/PC, barcode scanners, receipt printer, cash drawer, backup drives | $1,200 – $2,800 | Faster checkout and stock receiving; reduced manual work. | $2,800 saved in staff workload
Training | Pharmacist and staff training sessions | $400 – $1,000 | Smooth transition, efficient use of system. | Higher productivity (≈ $1,500)
Maintenance | Annual software updates, bug fixes, server hosting | $800 – $1,200 | Ensures system reliability and data security. | $2,200 saved from downtime
Administration | Current manual system (stock registers, spreadsheets, paper invoices, printing) | $1,500 annually | Eliminated with the new system → paperless records. | $1,500 saved
Customer Experience | Manual lookups and long queues waste customers’ time | – | Faster service, instant availability checks, improved customer satisfaction and loyalty. | Intangible but high value (≈ $2,000)
Summary
Total Estimated Costs (first year): $4,400 – $9,500
Total Estimated Annual Benefits/Savings: $11,500 – $13,500+
Payback Period: Within 6 to 9 months
Conclusion: The Pharmacy Sales and Stock Management System is economically feasible, with clear cost savings and long-term value.

## ورقة3
FINANCIAL BREAKDOWN & RETURN ON INVESTMENT (ROI)
A. Initial Investment Breakdown (First Year)
Cost Element | Min Cost ($) | Max Cost ($) | Avg Cost ($) | % of Total Budget
Software Development & Licenses | 2000 | 4500 | 3250 | 41.94%
Hardware & Equipment (POS, Scanners) | 1200 | 2800 | 2000 | 25.81%
Staff Training & Onboarding | 400 | 1000 | 700 | 9.032%
Annual System Maintenance & Support | 800 | 1200 | 1000 | 12.9%
Data Migration & Digital Archiving | 600 | 1000 | 800 | 10.32%
Total Investment Cost | 5000 | 10500 | 7750 | 100%
B. Annual Recurring Value & Cost Savings
Benefit Area | Min Savings ($) | Max Savings ($) | Avg Savings ($) | Contribution %
Elimination of Expiry & Billing Errors | 3500 | 5000 | 4250 | 30.8%
Staff Workload & Productivity Gains | 2800 | 4000 | 3400 | 24.64%
Reduction in System Downtime | 2200 | 2800 | 2500 | 18.12%
Paperless Admin & Operational Efficiency | 1500 | 1800 | 1650 | 11.96%
Customer Retention & Service Speed | 1500 | 2500 | 2000 | 14.49%
Total Annual Savings | 11500 | 16100 | 13800 | 100%
C. Key Performance Ratios & Metrics
Net Financial Benefit (Year 1) | Average Benefits - Average Costs | 6050
Return on Investment (ROI) | Net Financial Benefit / Average Costs | 78.06%
Payback Period | Total Average Costs / Total Average Benefits | 0.56159